## Hoja1
These hours have been counted once the delivery of the wiki has been made

	Person Average	Estimated Total Time	Real Total Time	Average error
	Rafa	71:10 h	87:35 h	-16.81 %
	Jose	58:15 h	80:05 h	-17.79 %
	Ferran	75:45 h	103:30 h	-21.69 %
	Adria	59:10 h	71:30 h	-22.07 %

Tasca	Persona Encarregada	Estimated Task Time	Real Task Time	Data d'implementació	Difference between estimated and real
Fixing background colliders	Adria	1h	1:45h	07/04/2019	2 h
Fixed camera scrolling	Adria	0:30h	0:15h	11/04/2019	1 h
Improving “add bounds to stage” function	Adria	1h	1:15h	11/04/2019	-0:30 h
Adding collision boxes to standing, forwards, backwards	Adria	2h	1:30h	19/04/19	0 h
Fixing camera (provisional, but working as intended)	Adria	1h	1:20h	21/04/19	0 h
Fixing stage sizes	Adria	0:10 h	0:20 h	21/04/19	0:15 h
Adding/Fixing Animations (idle, fwd,back,crouch,crouching,standing)	Adria	4h	3h	21/04/19	0 h
Add Fade out fade in	Adriá	0:30 h	0:45 h	07/04/2019	0 h
Fixing colliders detection	Adriá	0:30 h	1:10 h	09/04/2019	4 h
Players shouldnt move beyond camera	Adrià	0:35h	0:20h	08/04/2019	-0:15 h
Fixing detection formula	Adrià	0:20h	0:20h	11/04/2019	0:45h
Trying to fix camera (NOT SUCCESSFUL)	Adria, Jose	0:30h	4:30h	19/04/19	0:15 h
General improvement of code	Ferran	0:10 h	0:45 h	10/04/19	0:20 h
Fix Camera	Ferran	1 h	4 h	08/04/2019	0 h
Making collisions with projectiles	Ferran	2 h	4 h	07/04/2019	-0:15 h
Change module Honda for Sagat	Ferran	0:30 h	2 h	08/04/2019	0:15 h
Add hit type in colliders	Ferran	0:30 h	0:20 h	08/04/2019	0:30 h
Fix hitbox Hadoken Player 2	Ferran	1 h	0:45 h	06/04/2019	0:30 h
Put frames of each movement	Ferran	5 h	1:30 h	11/04/2019	-0:10 h
Fix objects in the front	Ferran	0:30 h	0:20 h	12/04/2019	-
Fix collisions with walls	Ferran	0:20 h	2:30 h	14/04/2019	0 h
Module font implemented	Ferran	0:30 h	0:45 h	15/04/2019	0:30 h
Semi-implementation of the time marker	Ferran	3 h	3 h	15/04/2019	2 h
Implementation of the UI and Blit of the KO icon	Ferran	1 h	3 h	16/04/2019	0:35 h
Treatment of time of tasks	Ferran	0:30 h	0:20 h	14/04/2019	0:10 h
Recompose the UI spritesheets	Ferran	3 h	4 h	18/04/2019	3 h
Life bar implementation	Ferran	5 h	2 h	19/04/2019	2 h
Add animation get up, air reel, win and lose	Ferran	3 h	5 h	27/04/2019	1:30 h
Calibrate the jumps	Ferran	2 h	1:30 h	27/04/2019	-0:10 h
Implement state machine in Player 2	Ferran, Jose	1 h	2:30 h	14/04/2019	-0:15 h
Add music to modules	Ferran, Jose, Adriá	2 h	3 h	31/03/2019	-3:30 h
Fix Jump	Jose	1 h	0:30 h	01/04/2019	-0:10h
Add Hadouken	Jose	2 h	2h	04/04/2019	2:10 h
Hit the opponent with hdk and animation	Jose	1 h	1 h	07/04/2019	1:30 h
Make players collide	Jose	0:30h	0:30h	07/04/2019	0:15 h
Add state machine	Jose	5 h	9 h	14/04/2019	0 h
Ken stage	Jose	3:00 h	5:00 h	09/04/2019	-1 h
Change orientation hadoken player 2	Jose	1h	1 h	16/04/19	-0:40 h
Redo Module Fonts and create module UI	Jose	4h	4:30h	22/04/19	0 h
Modify state box	Jose	4h	4h	26/04/19	2 h
Life bars movement	Jose	1h	2h	26/04/19	-0:10 h
Repeat animations	Jose	0:30 h	1:30h	28/04/19	0 h
Invisibility Hadouken	Jose	0:10 h	1:30h	28/04/19	0 h
Defeat animation	Jose	0:20 h	0:20 h	28/04/19	1 h
Fix hadoken (together)	Jose	0:15 h	0:30 h	28/04/19	-3 h
Fix jumps	Jose	1 h	0:45 h	28/04/19	-2 h
Drop	Jose	0:30 h	0:30 h	28/04/19	4 h
Fix jumps 2	Jose	0:30 h	0:30 h	28/04/19	-0:30 h
Crouching Reel	Jose	0:30 h	0:20 h	28/04/19	0:20 h
Win-Lose States	Jose	0:30h	0:30 h	28/04/19	0:10 h
Falling and getting up	Jose	1h	0:45 h	28/04/19	-1h
Add smart camera	Jose, Adri, Ferran	3 h	3 h	18/04/19	-0:30 h
Add Module Player 2	Jose, Ferran	1 h	1h	04/04/2019	0 h
Hitbox hdk	Jose, Ferran	0:30h	0:45 h	07/04/2019	-0:15 h
Fight Timer	Jose, Ferran	1h	0:20 h	16/04/19	0:30 h
Make background module for the scroll	Rafa	3 h	5 h	29/03/2019	0 h
Layout final project to do the tasks of Handout 5	Rafa	1:30 h	2h	31/03/2019	1 h
Make Welcome Page	Rafa	0:30 h	1h	31/03/2019	1:30 h
Make End Battle Screen	Rafa	0:30 h	0:20 h	31/03/2019	2 h
Correct commit errors Ferrán	Rafa	-	0:45 h	31/03/2019	2 h
Make the time of the animations count by frames	Rafa	1 h	1 h	11/04/2019	-0:30 h
Add logic to have different hitboxes in each frame	Rafa	3:00 h	3:30 h	13/04/2019	-0:15h
Add objet frame	Rafa	0:20 h	0:30 h	14/04/19	-0:10 h
Add logic to add and remove the hitboxes of each frame in the characters	Rafa	2 h	1 h	16/04/19	1 h
Move the images of the wiki to the new assets folder	Rafa	0:30 h	0:30 h	17/04/19	-0:15 h
Add pivots to each animation and add correct frame count	Rafa	5 h	3 h	19/04/19	-0:05 h
Add limits to players	Rafa	1 h	0:30 h	22/04/19	1:20 h
Repair Countdown	Rafa	2 h	2 h	22/04/19	0 h
Flip CollisionsBox and pivot	Rafa	2 h	1:45h	25/04/19	0:15 h
Add Module Fight and put logic to load the stage, player and interface	Rafa	4h	5:30h	26/04/19	-0:15 h
Put logic to the UI module so that it works with the fight module and put win and lose condition	Rafa	4h	6H	27/04/19	0 h
Add frames of invulnerability	Rafa	0:30 h	0:15h	28/04/2019	0 h
Correct teleportation in the jump	Rafa	0:20 h	0:10 h	28/04/2019	0 h
Push player without passing the limits	Rafa	0:45 h	1 h	28/04/19	-0:10 h
Add audios to the blows of both players	Rafa	0:30 h	0:25 h	28/04/19	-0:10 h
Fix bug different damages for both players	Rafa	0:15 h	0:15h	28/04/19	-0:30 h
Fix audio bug in player 2 jump	Rafa	0:20 h	0:10 h	28/04/19	0 h
Add colliders wall limit of the map and increase the invulnerabilities to 25 frames	Rafa	0:30 h	1 h	28/04/19	-0:15 h
Add reset to animations	Rafa	0:30 h	0:25 h	28/04/19	-0:05 h
Adding Dhalsim animations	Adrià	1:30h	2:30h	08/05/19	0:15 h
Dhalsim HK	Adrià	0:30h	1h	17/05/10	1:20 h
Adjusting Dhalsim Timers (all 6 normals, all 6 cr-normals)	Adrià	2h	4h	20/05/19	0:15 h
Adjusting almost all remaining Dhalsim Timers	Adrià	4h	4h	20/05/19	1:00h
Dhalsim pushback decent state	Adrià	2h	4h	22/05/19	-0:05 h
Font creation + misc	Adrià	3h	4:30h	27/05/19	-0:10 h
Fonts / Logic / Animation / Misc	Adrià	5h	5h	28/05/19	-0:05 h
Ending Fonts / sfx	Adrià	5h	4:30h	29/05/19	-2:00 h
Messing with fonts / sfx / endingbattle /startbattle	Adrià	5h	4:30h	30/05/19	0 h
Dhalsim animation, levitation logic, win pose logic	Adrià	4h	4:30h	31/05/19	-1:30h
Fixed multiple font issues both in code and in spritesheet	Adrià	4h	4h	01/06/19	-0:30h
Misic stuff (mostly helping and fixing TODO bugs)	Adrià	4:30h	4h	02/06/19	-1h
Fixed a couple font issues in debug function	Adrià	1:30h	1:30h	03/06/19	-2h
Dhalsim idle and forward animation implemented	Ferran	0:30 h	0:45 h	07/05/19	-0h
Dhalsim backward, lk and lp animation implemented	Ferran	1 h	2:20 h	08/05/19	1 h
Dhalsim neutral jump animation implemented	Ferran	0:30 h	0:45 h	08/05/19
Dhalsim reel animations	Ferran	1 h	0:55 h	11/05/19
Dhalsim victory animation	Ferran	0:40 h	0:30 h	11/05/19	1:15 h
Dhalsim jumping and jumping lk, lp animation	Ferran	2 h	1:55 h	11/05/19
Dhalsim close standing and crouching animations	Ferran	4 h	5 h	20/05/19	-2h
Adjusting / implementing Dhalsim specials and animations	Ferran	7 h	6 h	21/05/19
Adjust Dhalsim animations	Ferran	4 h	2:45 h	21/05/19	-0:30 h
Miscelanious Dhalsim animations	Ferran	1:30 h	2 h	23/05/19	-0:50 h
Shadows implementation and ripping	Ferran	2 h	2:50 h	27/05/19	-2h
Dhalsim animations timer fix	Ferran	4 h	5 h	29/05/19	0h
Put grab animation in spritesheets	Ferran	1h	0:30 h	28/05/19	-2h
Yoga flame reprogramming	Ferran	1 h	2:15 h	31/05/19	-2h
Add audio when hitting	Ferran	0:45 h	4 h	30/05/19	-1:30h
Crouching kick movement	Ferran	0:30 h	0:50 h	31/05/19	1 h
Yoga fire resize	Ferran	0:20 h	0:30 h	31/05/2019	-1h
Yoga fire and flame sound added	Ferran	1:30 h	3:20 h	01/06/19	0:30 h
Turning animation added	Ferran	0:40 h	0:50 h	02/06/19	-0:10 h
Attacking particles added	Ferran	5 h	13 h	07/06/2019	+0:30h
Burning animation added	Ferran	0:20 h	0:30 h	06/06/2019	+0:30h
Inputs 8 direcciones	Jose	4h	10 h	16/05/19	1h
Preparar caja estados para golpes medium, fierce y defender de pie	Jose	6h	7h	06/05/19	+0:30 h
Arreglar saltos	Jose	1h	1h	22/05/19	-1:15 h
Defending logic	Jose	0:30 h	0:20h	23/05/19	-3:15 h
Grabbed	Jose	1 h	2h	28/05/19	0h
Add special movements	Jose	3 h	4h	30/05/19	00:30:00
Crouching defending	Jose	2h	1:30 h	28/04/19	-0:20 h
Cuadrar los combos mejor	Jose	0:30 h	0:30h	31/05/19	0 h
Yoga drill y yoga mummy	Jose	1:30 h	1 h	31/05/19	-0:30h
make jumps better	Jose	1 h	1h	31/05/19	-0:30 h
State cage dizzi	Jose	1 h	1 : 30h	31/05/19	-0:10 h
Make Color variation for Dhalsim	Rafa	1 h	3 h	11/05/19	1:20 h
Add pivot to Dhalsim animations	Rafa	1 h	1 h	12/05/19
Move on Border Characters	Rafa	2 h	3:30 h	19/05/19	-1 h
Make new spritesheet for Character Selection	Rafa	2 h	4 h	30/05/19	-2:10 h
VS Screen and logic for End game screen	Rafa	4 h	4 h	29/05/19	-0:10 h
Intro Screen	Rafa	2 h	4 h	28/05/19	- 8 h
Esthetic of character selection and vs and end game screens	Rafa	4 h	6 h	30/05/19	-0:30h
Add Logic to character selection screen	Rafa	3 h	1:40h	01/06/19
New Spritesheet for UI and update the current elements of UI	Rafa	3 h	4 h	01/06/19	-0:10h
Add Puntuation for both players	Rafa	1h	1h	02/06/19	0 h
Post Fight UI	Rafa	3 h	4 h	02/06/19	-1 h
Create Web	Rafa	0:30 h	1 h	03/06/19	-0:30 h
Add read inputs from keyboard and gamepads	Rafa	2 h	1 : 30h	03/06/19	0:30 h
Add Camera shaking and slowdown	Rafa	3 h	3 h	04/06/19	0 h
Add Don't defend low attacks if dont defend in crouching	Rafa	1 h	1 : 30h	06/06/19	-0:30h
Clean memory leaks	Rafa	2 h	2 h	07/06/19	0 h
Created Build 0.9.1	Rafa	0:30 h	0:20 h	07/06/19	-0:10 h
Fix Dhalsim particles	Rafa	2 h	2 h	07/06/19	0 h
Add Opening	Rafa	4 h	5 h	08/06/19	1 h
Add Draw in fights	Rafa	3 h	5 h	08/06/19	2 h

Multiple animation adjustment (sprite, logic, state implementation) / Win logic adjustment	Adria	4h	4h	04/06/19
Debug capabilities / bool dizzi gestor / sfx spritesheet gestion	Adria	5h	4h	05/06/19	-1h

Sweep implementation /pushback logic / hitstop logic	Adria	5h	4h	07/06/19	-1h
Bug fixing / playtesting	Adria	7h	7h	08/06/19